## Summary
May, 2026 | Pool House - Building ($781,622) |  | Pool House -Expanded Coverage ($150,000) |  | Pool House - Personal Property ($546,000) |  | Pool Inventory (included under Pool coverage of $400,000) |  | Pool ($400,000) |  | Pool House - Business Interruption
| Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds
Insurance Proceeds - 4/25/24 |  | 781622 |  | 59396 |  | 91788 | [5 empty] | 0
Insurance Proceeds - 5/24/24 | [9 empty] | 11977.3
Insurance Proceeds - 6/26/24 | [11 empty] | 6080
Insurance Proceeds - 10/4/24 | [9 empty] | 19003
Insurance Proceeds - 2/4/25 |  |  |  | 39200 | [5 empty] | 6826 |  | 4241
Insurance Proceeds - 3/9/26 |  |  |  | 39982 |  | 75 |  |  |  | 2392 |  | 6891
Through June, 2024
TAP Security Fencing | [10 empty] | 1366
Traffic Signs - McCoy | 63
Power Pole - Gore | [8 empty] | 1350
Masonry Work - Maroff |  |  | 4000
Pool House Demo - Bellamy |  |  | 35200
TAP Security Fencing | 326
Pool House Mat'l - Goodwin | [8 empty] | 180
Drain Pool Repairs - Keenan | [8 empty] | 111
Drain Pool Repairs - Antisell | [8 empty] | 61
Pump House Mat'l - Antisell | 50
Pool pumps - Wooten Electric | [8 empty] | 8603
Skimmer lids - Antisell | 37
Supplies for safety equipment - Antisell | 32
Supplies to seal plywood - Antisell | 37
Reconnect Water Meter - Vic West | [8 empty] | 356
TAP Security Fencing | [10 empty] | 455 |  | 52227
Through July, 2024
Pump Room Gate - Keenan | [8 empty] | 141
TAP Security Fencing - credit for June | -326
BEMC Temporary Power | [8 empty] | 214
Pool Deck Fencing - Nat'l Construction | [8 empty] | 1334
BEMC Temporary Power | [8 empty] | 455
BEMC Pool Power | [10 empty] | 669
Temporary Toilets | [8 empty] | 320
Through August 31, 2024
BEMC Temporary Power | [10 empty] | 32
BBQ Grill | 1600
BEMC Temporary Power | [10 empty] | 13
Architect - Goodwin (Down Payment) | 7600
Pool Water - TSM | [8 empty] | 500
Temporary Toilets | [8 empty] | 320
Through September 30, 2024
Temporary Toilets | [8 empty] | 320
Survey | 2230
BEMC Temporary Power | [10 empty] | 32
Through October 31, 2024
Temporary Toilets | [10 empty] | 320
BEMC Temporary Power | [10 empty] | 32
Linens & Table Cloths |  |  |  |  | 752
Survey Copies | 32
Aqua Tech - pool cleaning after fire | [8 empty] | 4000
Aqua Tech - O ring feeder/30' pole | [6 empty] | 425
Aqua Tech - rebuild filter & lateral | [8 empty] | 847
Aqua Tech - rebuild 2 pump motors | [8 empty] | 4063
Aqua Tech - lift chair | [6 empty] | 7654
Through November 30, 2024
BEMC Temporary Power | [10 empty] | 32
Lift Chair Cover - Antisell | [6 empty] | 106
Through December 31, 2024
Triangle Fencing - Construction Site | [10 empty] | 208
Aquatech - replace flow filter | [8 empty] | 555
Aquatech - repair feeders & plumbing | [8 empty] | 207
Aquatech - cleaning | [8 empty] | 400
Aquatech - replace water valve | [8 empty] | 139
Aquatech - repair backwash line | [8 empty] | 188
BEMC Temporary Power | [10 empty] | 32
National Constuction - 1 yr fence renewal | [10 empty] | 749
Aquatech - remove damaged output plumbing | [8 empty] | 623
Through January 31, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
BEMC Temporary Power | [10 empty] | 32
Through February 28, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
BEMC Temporary Power | [10 empty] | 32
Architect - Goodwin | 24000
Through March 31, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
BEMC Temporary Power | [10 empty] | 32
Through April 30, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Triangle Fencing - Construction Site | [10 empty] | 267
BEMC Temporary Power | [10 empty] | 32
BRUNSCO Hydrant Flow Test | 500
Tables for Pool - Antisell |  |  |  |  | 75
Through May 31, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets | [8 empty] | 320
BEMC Temporary Power | [10 empty] | 32
Pinnacle Southeast - down payment | 113312
Through June 30, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets | [8 empty] | 320
BEMC Temporary Power | [10 empty] | 32 |  | 177406
Through July 31, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets | [8 empty] | 320
BEMC Temporary Power | [10 empty] | 33
Through August 31, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets | [8 empty] | 320
BEMC Temporary Power | [10 empty] | 33
Through September 30, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets - Elvis | [8 empty] | 105
BEMC Temporary Power | [10 empty] | 33
Through October 31, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets - Elvis | [8 empty] | 324
BEMC Temporary Power | [10 empty] | 33
Through November 30, 2025
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets - Elvis | [8 empty] | 324
BEMC Temporary Power | [10 empty] | 33
Through December 31, 2025
Triangle Fencing - Construction Site | [10 empty] | 564
Temporary Toilets - Elvis | [8 empty] | 105
BEMC Temporary Power | [10 empty] | 38
Through January 31, 2026 | [13 empty] | 52227
Triangle Fencing - Construction Site | [10 empty] | 534 |  |  | 177406
BEMC Temporary Power | [10 empty] | 38 |  |  | 4515
Through February 28, 2026 | [13 empty] | 234148
Triangle Fencing - Construction Site | [10 empty] | 267 |  |  | 7900
BEMC Temporary Power | [10 empty] | 38 |  |  | 242048
Through March 31, 2026
BEMC Temporary Power | [10 empty] | 38
Through April 30, 2026
Triangle Fencing - Construction Site | [10 empty] | 267
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets - Elvis | [8 empty] | 358
BEMC Temporary Power | [10 empty] | 38
Through May 31, 2026
Triangle Fencing - Construction Site | [10 empty] | 267
Temporary Toilets - Elvis | [8 empty] | 283
BEMC Temporary Power | [10 empty] | 38
Through June 30, 2026
Triangle Fencing - Construction Site | [10 empty] | 267
BEMC Temporary Power | [10 empty] | 38
Temporary Toilets - Elvis | [8 empty] | 358
Grass Roots Landscaping |  |  | 180
Pinnacle Southeast - Draw #2 | 91030
Committed - Architect | 7900
Total
Total Spent / Committed | 248423 |  | 39380 |  | 827 |  | 8185 |  | 28424 |  | 10200 |  | 335439
Proceeds Remaining |  | 533199 |  | 99198 |  | 91036 |  |  |  | 3589.3 |  | 7012
Total Funds Available | 1069473.3
Total Funds Remaining | 734034.3
Upon Project Completion: | [6 empty] | = submitted on Supplemental Claim #1
Depreciation | 52034 | [5 empty] | = submitted on Supplemental Claim #2
Code Upgrades (sprinklers, asphalt, civil) | 110800 | [5 empty] | = submitted on Supplemental Claim #3
Totsl | 162834 | ** |  |  |  |  | = POA expense (post 2 yr anniversary) |  |  |  | check | -327539
** amount is not included in the reconciliation; this will be disbursed after project completion
Note on K4: Mike Collins: includes ADA Lift Chair for pool & deck repairs
Note on E8: Mike Collins: $22.282 landscaping $1,200 signage $16,500 fence
Note on B21: Mike Collins: paid in original claim
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LFCC grill lost in fire
Note on L59: Mike Collins: invoice shows 266.88; credit issued; ME requesting a copy
Note on B141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Balance due architect $38 - 7.6 (down payment) + 1,5 (change order) - 24 (payment)

## Sheet1 (hidden)
[5 empty] | Total Project Cost |  | Approximate Project Cost
spent/committed |  |  | spent |  | Hewett Quote | 1426489 | Hewett Quote | 1426489
Insurance Proceeds | 1069473.3 |  | Insurance Proceeds | 1069473.3 | 10% Down Payment | -107456 | 10% Contingency | 142649
Spent/Committed | 335439 |  | Spent | 327539 | 10% Contingency | 142649 | Costs Incurred Outside of Construction Contract
Funds Remaining | 734034.3 |  | Funds Remaining | 741934.3 | Spent as of 3/31/26: |  | Goodwin (archtect) | 39500
[5 empty] | Goodwin (archtect) | 39500 | Bellamy (demolition) | 39200
| check | 7900 |  |  | Bellamy (demolition) | 39200 | Fencing, Pump Room, Survey, etc. | 52397
[5 empty] | Down Payment | 107456 | Additional Costs (outside of the Hewett quote):
costs-down payment-architect-demo (for project cost calculation) |  |  |  |  | Fencing, Pump Room, Survey, etc. | 47992 | Landscaping | 22282
52397 |  |  |  |  | Additional Costs (outside of the Hewett quote): |  | Pool Fencing | 16500
[5 empty] | Landscaping | 22282 | Pool Signage | 1200
[5 empty] | Pool Fencing | 16500 | Furnishings | 91788
[5 empty] | Pool Signage | 1200
[5 empty] | Furnishings | 91788 | Approximate Project Cost Total | 1832005
[5 empty] | Total Project Cost | 1827600
*

## Summary Community #1
Budget for Pool House (Expenses Incurred vs Insurance Proceeds) w Estimate of Total Project Costs
As of 6/30/26
| Pool House - Building |  | Pool House -Expanded Coverage |  | Pool House - Personal Property |  | Pool Inventory |  | Pool House - Business Interruption
| Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds
Insurance Proceeds - 4/25/24 |  | 781622 |  | 59396 |  | 91788 |  |  |  | 0
Insurance Proceeds - 5/24/24 | [7 empty] | 11977.3
Insurance Proceeds - 6/26/24 | [9 empty] | 6080
Insurance Proceeds - 10/4/24 | [7 empty] | 19003
Insurance Proceeds - 2/4/25 |  |  |  | 39200 |  |  |  | 6826 |  | 4241
Insurance Proceeds - 3/9/26 |  |  |  | 39982 |  | 75 |  | 2392 |  | 6891
Costs Incurred To Date
| Signs |  | Demolition |  | Pool Furniture |  | Pool Lift Chair |  | Business Interruption
| Fencing |  |  |  | Linens |  | Pool Material
| Pump Room | [5 empty] | Pool Cleaning
| Architect | [5 empty] | Temp Toilets
| Survey | [5 empty] | Temp Power
| Flow Test | [5 empty] | Pool Repairs
| Down Payment - Draw #1 | [5 empty] | Pool Pumps
| Draw #2 | [5 empty] | Water Meter
Fencing
Total
Total Spent / Committed | 248423 |  | 39380 |  | 827 |  | 36609 |  | 10200 |  | 335439
Proceeds Remaining |  | 533199 |  | 99198 |  | 91036 |  | 3589.3 |  | 7012
Total Funds Available | 1069473.3
Total Funds Remaining | 734034.3
Upon Project Completion:
Depreciation | 52034
Code Upgrades (sprinklers, asphalt, civil) | 110800
** amount is not included in the reconciliation; this will be disbursed after project completion |  |  | 162834
Approximate Project Cost
Hewett Quote | 1426489
10% Contingency | 142649
Costs Incurred & Paid Outside of the Construction Contract
Goodwin (architect) | 39500
Bellamy (demolition) | 39200
Fencing, Pump Room, Survey, etc. | 52397
Additional Costs (outside of the Construction Contract):
Landscaping | 22282
Pool Fencing | 16500
Pool Signage | 1200
Furnishings | 91788
Approximate Project Cost Total | 1832005
Note on I6: Mike Collins: includes ADA Lift Chair for pool & deck repairs

## Summary Community - original (hidden)
Budget for Pool House (Expenses Incurred vs Insurance Proceeds)
As of 4/30/26
| Pool House - Building |  | Pool House -Expanded Coverage |  | Pool House - Personal Property |  | Pool Inventory |  | Pool House - Business Interruption
| Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds
Insurance Proceeds - 4/25/24 |  | 781622 |  | 59396 |  | 91788 |  |  |  | 0
Insurance Proceeds - 5/24/24 | [7 empty] | 11977.3
Insurance Proceeds - 6/26/24 | [9 empty] | 6080
Insurance Proceeds - 10/4/24 | [7 empty] | 19003
Insurance Proceeds - 2/4/25 |  |  |  | 39200 |  |  |  | 6826 |  | 4241
Insurance Proceeds - 3/9/26 |  |  |  | 39982 |  | 75 |  | 2392 |  | 6891
Costs Incurred through 4/30/26:
| Signs |  | Demolition |  | Pool Furniture |  | Pool Lift Chair |  | Business Interruption
| Fencing |  |  |  | Linens |  | Pool Material
| Pump Room | [5 empty] | Pool Cleaning
| Architect | [5 empty] | Temp Toilets
| Survey | [5 empty] | Temp Power
| Flow Test | [5 empty] | Pool Repairs
| Down Payment | [5 empty] | Pool Pumps
Water Meter
Fencing
Total
Total Spent / Committed | 248423 |  | 39380 |  | 827 |  | 36609 |  | 10200 |  | 335439
Proceeds Remaining |  | 533199 |  | 99198 |  | 91036 |  | 3589.3 |  | 7012
Total Funds Available | 1069473.3
Total Funds Remaining | 734034.3
Upon Project Completion:
Depreciation | 52034
Code Upgrades (sprinklers, asphalt, civil) | 110800
** amount is not included in the reconciliation; this will be disbursed after project completion |  |  | 162834
Note on I6: Mike Collins: includes ADA Lift Chair for pool & deck repairs