## Sheet1
Budget for Pool House (Expenses Incurred vs Insurance Proceeds) w Estimate of Total Project Costs
As of 7/31/26
| Pool House - Building |  | Pool House -Expanded Coverage |  | Pool House - Personal Property |  | Pool Inventory |  | Pool House - Business Interruption
| Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds | Spent / Committed | Proceeds
Insurance Proceeds - 4/25/24 |  | 781622 |  | 59396 |  | 91788 |  |  |  | 0
Insurance Proceeds - 5/24/24 | [7 empty] | 11977.3
Insurance Proceeds - 6/26/24 | [9 empty] | 6080
Insurance Proceeds - 10/4/24 | [7 empty] | 19003
Insurance Proceeds - 2/4/25 |  |  |  | 39200 |  |  |  | 6826 |  | 4241
Insurance Proceeds - 3/9/26 |  |  |  | 39982 |  | 75 |  | 2392 |  | 6891
Costs Incurred To Date
| Signs |  | Demolition |  | Pool Furniture |  | Pool Lift Chair |  | Business Interruption
| Fencing |  |  |  | Linens |  | Pool Material
| Pump Room | [5 empty] | Pool Cleaning
| Architect | [5 empty] | Temp Toilets
| Survey | [5 empty] | Temp Power
| Flow Test | [5 empty] | Pool Repairs
| Down Payment - Draw #1 | [5 empty] | Pool Pumps
| Draw #2 | [5 empty] | Water Meter
Fencing
Total
Total Spent / Committed | 248423 |  | 39380 |  | 827 |  | 36967 |  | 11069 |  | 336666
Proceeds Remaining |  | 533199 |  | 99198 |  | 91036 |  | 3231.3 |  | 6143
Total Funds Available | 1069473.3
Total Funds Remaining | 732807.3
Upon Project Completion:
Depreciation | 52034
Code Upgrades (sprinklers, asphalt, civil) | 110800
** amount is not included in the reconciliation; this will be disbursed after project completion |  |  | 162834
Approximate Project Cost
Hewett Quote | 1426489 |  | Notes on Approximate Project Costs
10% Contingency | 142649 |  | - | costs are ESTIMATES except for architectural fees, demolition & miscellaneous costs
Costs Incurred & Paid Outside of the Construction Contract |  |  | - | the construction contract includes a builder's contingency fee & allowances
Goodwin (architect) | 39500 |  | - | the Association is owed $163k from insurance upon project completion
Bellamy (demolition) | 39200 |  | - | there is an Association contingency of $143k build into the projection
Fencing, Pump Room, Survey, etc. | 53624 |  | - | the cost of furnishings, $92k, is what the Association received from insurance and is not
Additional Costs (outside of the Construction Contract): |  |  |  |  | necessarily the amount that will be spent
Landscaping | 22282
Pool Fencing | 16500
Pool Signage | 1200
Furnishings | 91788
Approximate Project Cost Total | 1833232
Note on I6: Mike Collins: includes ADA Lift Chair for pool & deck repairs